## blog
[7 empty] | Team Members | [10 empty] | Instructions: Fill in only the green portions. For the activities table, put number 1 in the square under each name if that individual participated in that activity. The number of hours for each individual will be calculated automatically. Adjust the cell size to ensure all text is visible as needed. Add more rows as necessary
[7 empty] | First Name | Last Name | Nickname (max 6 characters)
[7 empty] | Sawaab | Anas | SA
[7 empty] | Manahil | Bashir | MB
[7 empty] | Mary Joleene | Ismael | MJI
[7 empty] | Asmah Yasin | Mohamed | AYM
[7 empty] | Muqadas | Nazif | MN
[7 empty] | Efetobore | Salubi | ES
Activities Table
Date | Who | [5 empty] | Type of Activty | Number of hours spent | Purpose | Output | Hours spent
| SA | MB | MJI | AYM | MN | ES |  |  |  |  | SA | MB | MJI | AYM | MN | ES
Milestone 1
2025-09-23 | 1 | 1 | 1 | 1 | 1 | 1 | Meeting | 1.5 | Select a project and establish goals | Custom project selected, and initial scope outlined | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
2025-09-26 | 1 | 1 | 1 | 1 | 1 | 1 | Work remotely | 1 | Completion of project document for submission | Submit project milestone | 1 | 1 | 1 | 1 | 1 | 1
[10 empty] | Total hours | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
[10 empty] | Total team hours | [6 empty] | 15
Milestone 2
2025-10-08 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | Discuss project and divide tasks among group members | Roles assigned; timeline agreed | 1 | 1 | 1 | 1 | 1 | 1
2025-10-10 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | Working on assigned tasks remotely | Project is ready for submission | 1 | 1 | 1 | 1 | 1 | 1
[10 empty] | Total hours | 2 | 2 | 2 | 2 | 2 | 2
[10 empty] | Total team hours | [6 empty] | 12
Sprint 1
2025-10-23 | 1 | 1 | 1 | 1 | 1 | 1 |  | 3 | Sprint planning | Plan sprint goals and assign backlog items | 3 | 3 | 3 | 3 | 3 | 3
2025-10-24 | 2 | 1 | 1 | 1 | 1 | 1 |  | 2.5 | Coding and development | Project environment set up. Initial coding and testing in progress | 5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
2025-10-25 | 1 | 1 | 1 | 1 | 1 | 3 |  | 3.5 | Coding and development | Implementation and testing | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 10.5
2025-10-26 | 1 | 1 | 1 | 1 | 1 | 1 |  | 2 | Coding and development | Implementation and testing | 2 | 2 | 2 | 2 | 2 | 2
2025-10-27 | 1 | 1 | 1 | 1 | 1 | 1 |  | 2.5 | Sprint Review | Work submission. Reflect and improve team process | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
[10 empty] | Total hours | 16 | 13.5 | 13.5 | 13.5 | 13.5 | 20.5
[10 empty] | Total team hours | [6 empty] | 90.5
Sprint 2
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Total hours | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Total Team hours | [6 empty] | 0
Sprint 3
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Total hours | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | total team hours | [6 empty] | 0
[10 empty] | Total hour over project | 20.5 | 18 | 18 | 18 | 18 | 25
[10 empty] | Total team hours over project | [6 empty] | 117.5