## blog
[7 empty] | Team Members | [10 empty] | Instructions: Fill in only the green portions. For the activities table, put number 1 in the square under each name if that individual participated in that activity. The number of hours for each individual will be calculated automatically. Adjust the cell size to ensure all text is visible as needed. Add more rows as necessary
[7 empty] | First Name | Last Name | Nickname (max 6 characters)
[7 empty] | Sawaab | Anas | SA
[7 empty] | Manahil | Bashir | MB
[7 empty] | Mary Joleene | Ismael | MJI
[7 empty] | Asmah Yasin | Mohamed | AYM
[7 empty] | Muqadas | Nazif | MN
[7 empty] | Efetobore | Salubi | ES
Activities Table
Date | Who | [5 empty] | Type of Activty | Number of hours spent | Purpose | Output | Hours spent
| SA | MB | MJI | AYM | MN | ES |  |  |  |  | SA | MB | MJI | AYM | MN | ES
Milestone 1
2025-09-23 | 1 | 1 | 1 | 1 | 1 | 1 | Meeting | 1.5 | Select a project and establish goals | Custom project selected, and initial scope outlined | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
2025-09-26 | 1 | 1 | 1 | 1 | 1 | 1 | Work remotely | 1 | Completion of project document for submission | Submit project milestone | 1 | 1 | 1 | 1 | 1 | 1
[10 empty] | Total hours | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
[10 empty] | Total team hours | [6 empty] | 15
Milestone 2
2025-10-08 | 1 | 1 | 1 | 1 | 1 | 1 | Meeting | 1 | Discuss project and divide tasks among group members | Roles assigned; timeline agreed | 1 | 1 | 1 | 1 | 1 | 1
2025-10-10 | 1 | 1 | 1 | 1 | 1 | 1 | Work remotely | 1 | Working on assigned tasks remotely | Project is ready for submission | 1 | 1 | 1 | 1 | 1 | 1
[10 empty] | Total hours | 2 | 2 | 2 | 2 | 2 | 2
[10 empty] | Total team hours | [6 empty] | 12
Sprint 1
2025-10-23 | 1 | 1 | 1 | 1 | 1 | 1 | Meeting | 3 | Sprint planning | Plan sprint goals and assign backlog items | 3 | 3 | 3 | 3 | 3 | 3
2025-10-24 | 1 | 1 | 1 | 1 | 1 | 1 | Work remotely | 2.5 | Coding and development | Project environment set up. Initial coding and testing in progress | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
2025-10-25 | 1 | 1 | 1 | 1 | 1 | 1 | Work remotely | 3.5 | Coding and development | Implementation and testing | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5
2025-10-26 | 1 | 1 | 1 | 1 | 1 | 1 | Work remotely | 2 | Coding and development | Implementation and testing | 2 | 2 | 2 | 2 | 2 | 2
2025-10-27 | 1 | 1 | 1 | 1 | 1 | 1 | Meeting | 2.5 | Sprint Review | Reflect and improve team process | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
2025-10-28 | 1 | 1 | 1 | 1 | 1 | 1 | Work remotely | 1.5 | Submission extended. Restructure GitHub files | Submit sprint 1 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
[10 empty] | Total hours | 15 | 15 | 15 | 15 | 15 | 15
[10 empty] | Total team hours | [6 empty] | 90
Sprint 2
2025-11-04 | 1 | 1 | 1 | 1 | 1 | 1 | In-person meeting | 2 | Sprint planning | Reflect on previous sprint and assign backlog items | 2 | 2 | 1 | 2 | 4 | 2
2025-11-06 | 1 | 1 | 1 | 1 | 1 | 1 | In-person meeting | 3 | Coding and Implementation | Work in progress | 3 | 3 | 3 | 2 | 3 | 3
2025-11-08 | 1 | 1 | 1 | 1 | 1 | 1 | Work remotely | 5 | Coding and Implementation | Work in progress | 8 | 3 | 5 | 6 | 5 | 5
2025-11-09 | 1 | 1 | 1 | 1 | 1 | 1 | Work remotely | 5 | Review and refine code | Sprint ready for submission | 5 | 5 | 5 | 5 | 5 | 5
[10 empty] | Total hours | 18 | 13 | 14 | 15 | 17 | 15
[10 empty] | Total Team hours | [6 empty] | 92
Sprint 3
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Total hours | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | total team hours | [6 empty] | 0
[10 empty] | Total hour over project | 37.5 | 32.5 | 33.5 | 34.5 | 36.5 | 34.5
[10 empty] | Total team hours over project | [6 empty] | 209