## Cover Page
<Laurier Club Room Booking System>
Prepared By:Sawaab Anas
Team 6
<Sawaab Anas>: <169064564>
<Muqadas Nazif>: <169061218>
<Manahil Bashir>: <169061137>
<Efetobore Salubi>: <169109324>
<Joleene Ismael>: <169044811>
<Asmah Yasin Mohamed>: <169076868>

## Product Backlog
Product Backlog
Story ID | Story Title | Card | Story Points | Priority | Sprint | Status | Conversation | Confirmation
Story ID | Story Title | Card (User Story) | Story Points | Priority | Sprint | Status | Conversation | Confirmation (Acceptance Criteria)
AUTH-1 | User Authentication | As a user, I want to log in securely using my Laurier credentials so that only authorized users can make bookings. | 5 | High | Sprint 1 | Not Started | Discussed Single Sign-On vs. local account. Ie adding the @mylaurier con | Login/Logout works; unauthorized users blocked.
UI-1 | Search Availability | As a club member, I want to search rooms by date, time, capacity, and equipment so that I can find a suitable space for my event. | 5 | High | Sprint 1 | Not Started | Confirm which filters (date, time, capacity, equipment) to include. | User can filter and view rooms that meet all criteria.
UI-2 | Request Booking | As a club executive, I want to submit a room booking request so that I can secure a space for my club’s meeting. | 8 | High | Sprint 1 | Not Started | Discuss validation and auto-email confirmation. | Booking stored in DB; email sent to user and admin.
DB-1 | Save Booking Data | As a developer, I want all bookings saved in a centralized database so that data is retained. | 5 | High | Sprint 1 | Not Started | Choose DB type and schema. | All bookings persist in database and can be retrieved.
UI-4 | View My Bookings | As a club member, I want to see a list of my upcoming and past bookings so that I can stay organized. | 5 | Medium | Sprint 1 | Not Started | Confirm date sorting order. | Table displays bookings with status (upcoming, past).
UI-3 | Cancel Booking | As a club executive, I want to cancel an existing booking so that the room becomes available for others. | 3 | Medium | Sprint 2 | Not Started | Add confirmation popup for cancellation. | Room slot freed and notification sent.
ADM-1 | Approve / Decline Request | As an administrator, I want to approve or decline booking requests so that I can ensure fair and proper use. | 5 | High | Sprint 2 | Not Started | Design admin dashboard layout. | Status updates visible to both admin and requester.
ADM-2 | Set Booking Policies | As an administrator, I want to set limits on bookings per week so that no group monopolizes rooms. | 8 | High | Sprint 2 | Not Started | Confirm weekly quota values. | Policy prevents excess requests and gives clear error.
NOTIF-1 | Status Notifications | As a user, I want to receive notifications when my booking is approved, declined, or modified so that I stay informed. | 3 | High | Sprint 2 | Not Started | Clarify channels (email + in-app). | Notification sent for each booking update.
ADM-3 | Override Booking | As an administrator, I want to override an existing booking so that I can allocate a room for a priority event. | 5 | Medium | Sprint 3 | Not Started | Confirm audit trail logging. | Override replaces existing booking and logs event.
UI-5 | Recurring Booking | As a club executive, I want to book a room for recurring meetings so that I don’t have to re-enter details each week. | 8 | Medium | Sprint 3 | Not Started | Discuss recurrence options (weekly/monthly). | Series of bookings auto-created with correct intervals.
REP-1 | Room Utilization Report | As an admin, I want to see reports on room usage by day/time so I can identify high-demand spaces. | 8 | Medium | Sprint 3 | Not Started | Choose visualization type (chart/table). | Report accurately summarizes room usage trends.
UI-6 | Accessibility Enhancements | As a user with disabilities, I want screen-reader and high-contrast mode so I can use the app easily. | 3 | Medium | Sprint 3 | Not Started | Review WCAG 2.1 compliance. | App readable by screen readers and passes contrast tests.
Milestone 02 should now include:
Story ID, Title, Card (User Story) – already from Milestone 01 (You may add, or break down some of the story)
Story Points – estimated effort (e.g., 1, 3, 5, 8 using Fibonacci scale)
Priority (High, Medium, Low)
Sprint – which sprint it belongs to (Sprint 1, 2, or 3), the original Sprint
Status – Not Started, In Progress, or Done
Conversation – clarifications or notes from team discussions
Confirmation – acceptance criteria (how to know the story is “done”)
Note: The Fibonacci scale is a system of Agile estimation that uses numbers from the Fibonacci sequence (typically 0, 1, 2, 3, 5, 8, 13, 21, etc.) to assign story points to user stories and tasks.
This scale reflects an exponential increase in effort for more complex tasks and helps teams account for the growing uncertainty in estimating larger work.

## Sprint 1
Sprint 1 Backlog
Sprint 1 Goal(s): <Describe what you would like to achieve at the end of sprint 1>
Story ID | Task ID | Task Title | Task Description | Ideal Hours | Status | Comments
Story ID | Task ID | Task Title | Task Description | Ideal Hours | Status | Comments
AUTH-1 | AUTH-1.1 | Build Home & Navigation | Create base homepage layout; show Login/Signup; link to Browse Rooms page. | 3 | In Progress | Core navigation implemented
AUTH-1 | AUTH-1.2 | Login Page (myLaurier validation) | Create simple login page and restrict access to @mylaurier.ca emails; store session in localStorage. | 4 | Completed | Works without backend
UI-2 | UI-2.2 | Protected Routes | Prevent un-authenticated users from accessing booking pages; redirect to login. | 3 | Completed | Pending routing finalization
UI-1 | UI-1.1 | Room Booking Form | Create UI to allow user to select a room + book a timeslot; store booking locally. | 6 | Completed(need to remake) | Will integrate with local storage first
DB-1 | DB-1.1 | Save Booking Data | create a database to store user data and room data | 10 | Completed | set up and link 3 firestone database's
UI-4 | UI-4 | View My Bookings | Room booking to be linked to user ID | 3 | Completed | N./A