## Cover Page
<Laurier Club Room Booking System>
Prepared By:Sawaab Anas
Team 6
<Sawaab Anas>: <169064564>
<Muqadas Nazif>: <169061218>
<Manahil Bashir>: <169061137>
<Efetobore Salubi>: <169109324>
<Joleene Ismael>: <169044811>
<Asmah Yasin Mohamed>: <169076868>

## Product Backlog
Product Backlog
Story ID | Story Title | Card | Story Points | Priority | Sprint | Status | Conversation | Confirmation
Story ID | Story Title | Card (User Story) | Story Points | Priority | Sprint | Status | Conversation | Confirmation (Acceptance Criteria)
AUTH-1 | User Authentication | As a user, I want to log in securely using my Laurier credentials so that only authorized users can make bookings. | 5 | High | Sprint 1 | DONE | Discussed Single Sign-On vs. local account. Ie adding the @mylaurier con | Login/Logout works; unauthorized users blocked.
UI-1 | Search Availability | As a club member, I want to search rooms by date, time, capacity, and equipment so that I can find a suitable space for my event. | 5 | High | Sprint 1 | DONE | Confirm which filters (date, time, capacity, equipment) to include. | User can filter and view rooms that meet all criteria.
UI-2 | Request Booking | As a club executive, I want to submit a room booking request so that I can secure a space for my club’s meeting. | 8 | High | Sprint 1 | DONE | Discuss validation and auto-email confirmation. | Booking stored in DB; email sent to user and admin.
DB-1 | Save Booking Data | As a developer, I want all bookings saved in a centralized database so that data is retained. | 5 | High | Sprint 1 | DONE | Choose DB type and schema. | All bookings persist in database and can be retrieved.
UI-4 | View My Bookings | As a club member, I want to see a list of my upcoming and past bookings so that I can stay organized. | 5 | Medium | Sprint 1 | DONE | Confirm date sorting order. | Table displays bookings with status (upcoming, past).
UI-3 | Cancel Booking | As a club executive, I want to cancel an existing booking so that the room becomes available for others. | 3 | Medium | Sprint 2 | DONE | Add confirmation popup for cancellation. | Room slot freed and notification sent.
ADM-1 | Approve / Decline Request | As an administrator, I want to approve or decline booking requests so that I can ensure fair and proper use. | 5 | High | Sprint 2 | DONE | Design admin dashboard layout. | Status updates visible to both admin and requester.
ADM-2 | Set Booking Policies | As an administrator, I want to set limits on bookings per week so that no group monopolizes rooms. | 8 | High | Sprint 2 | DONE | Confirm weekly quota values. | Policy prevents excess requests and gives clear error.
UX-1 | UX Update — Figma Redesign | As a user, I want a cleaner and more intuitive page layout so that I can browse and book rooms without confusion. | 3 | Medium | Sprint 2 | DONE | Discussed improving layout flow, spacing, and visuals; need consistency in components and color palette. | Figma mockups finalized; navigation flows clear; shared with team for review.
UX-2 | UX Update — Frontend Build | As a user, I want the updated UI implemented so that the website matches the new Figma experience and feels professional. | 5 | Medium | Sprint 2 | DONE | Pending completion of UX-1; will include updated typography, spacing, and responsive structure. | Updated UI implemented; matches Figma; responsive across desktop & mobile.
NOTIF-1 | Status Notifications | As a user, I want to receive notifications when my booking is approved, declined, or modified so that I stay informed. | 3 | High | Sprint 2 | DONE | Clarify channels (email + in-app). | Notification sent for each booking update.
ADM-3 | Override Booking | As an administrator, I want to override an existing booking so that I can allocate a room for a priority event. | 5 | Medium | Sprint 3 | DONE | Confirm audit trail logging. | Override replaces existing booking and logs event.
UI-5 | Recurring Booking | As a club executive, I want to book a room for recurring meetings so that I don’t have to re-enter details each week. | 8 | Medium | Sprint 3 | DONE | Discuss recurrence options (weekly/monthly). | Series of bookings auto-created with correct intervals.
REP-1 | Room Utilization Report | As an admin, I want to see reports on room usage by day/time so I can identify high-demand spaces. | 8 | Medium | Sprint 3 | DONE | Choose visualization type (chart/table). | Report accurately summarizes room usage trends.
UI-6 | Accessibility Enhancements | As a user with disabilities, I want screen-reader and high-contrast mode so I can use the app easily. | 3 | Medium | Sprint 3 | DONE | Review WCAG 2.1 compliance. | App readable by screen readers and passes contrast tests.
UX-1 | UX-1 | UX Update — Figma Redesign | 3 | Medium | Sprint 2 | DONE | n/a | n/a
UX-2 | UX-2 | UX Update — Frontend Build | 3 | Medium | Sprint 2 | DONE | n/a | n/a
DASH-1 | Dashboard Overview | As a user, I want a dashboard that shows my weekly timetable and the next upcoming event so I can quickly see my schedule. | 5 | Medium | Sprint 3 | DONE | Discuss layout (timetable + upcoming event widget). | Dashboard displays timetable and correctly identifies next event.

## Sprint 1
Sprint 1 Backlog
Sprint 1 Goal(s): <Describe what you would like to achieve at the end of sprint 1>
Story ID | Task ID | Task Title | Task Description | Ideal Hours | Status | Comments
Story ID | Task ID | Task Title | Task Description | Ideal Hours | Status | Comments
AUTH-1 | AUTH-1.1 | Build Home & Navigation | Create base homepage layout; show Login/Signup; link to Browse Rooms page. | 3 | In Progress | Core navigation implemented
AUTH-1 | AUTH-1.2 | Login Page (myLaurier validation) | Create simple login page and restrict access to @mylaurier.ca emails; store session in localStorage. | 4 | Completed | Works without backend
UI-2 | UI-2.2 | Protected Routes | Prevent un-authenticated users from accessing booking pages; redirect to login. | 3 | Completed | Pending routing finalization
UI-1 | UI-1.1 | Room Booking Form | Create UI to allow user to select a room + book a timeslot; store booking locally. | 6 | Completed(need to remake) | Will integrate with local storage first
DB-1 | DB-1.1 | Save Booking Data | create a database to store user data and room data | 10 | Completed | set up and link 3 firestone database's
UI-4 | UI-4 | View My Bookings | Room booking to be linked to user ID | 3 | Completed | N./A

## Sprint 2
Sprint 1 Backlog
Sprint 1 Goal(s): <Describe what you would like to achieve at the end of sprint 1>
Story ID | Task ID | Task Title | Task Description | Ideal Hours | Status | Comments
Story ID | Task ID | Task Title | Task Description | Ideal Hours | Status | Comments
AUTH-1 | AUTH-1.1 | Build Home & Navigation | Create base homepage layout; show Login/Signup; link to Browse Rooms page. | 3 | Completed | Core navigation implemented; UX is simple but functional
UI-1 | UI-1.1 | Room Booking Form | Create UI to allow user to select a room + book a timeslot; store booking locally. | 6 | Completed | Local storage integration pending; UI tested with sample data
UI-3 | UI-3 | Cancel Booking | Allow user to delete their booking. | 2 | Completed | Tested basic flow; needs toast feedback later
ADM-1 | ADM-1 | Approve / Decline Request | Admin can approve/decline bookings; updates shown to user; admin can message user regardless of approval status. | 9 | Completed | Messaging works; UI could be cleaned later
ADM-2 | ADM-2 | Set Booking Policies | Add database rules: users can book only twice/week for up to 4 hours; must be an executive member to proceed. | 7 | Completed | Validations added; needs edge-case testing
NOTIF-1 | NOTIF-1 | Status Notifications | When admin accepts, notify the user via popup or UI update on user side. | 2 | Completed (minor updates later) | Basic notification implemented; styling pending
UX-1 | UX-1 | UX Update — Figma Redesign | Create an improved Figma design for the booking system — cleaner layouts, updated colour palette, and components for admin + user. | 6 | Completed | Wireframes complete; final UI components being refined
UX-2 | UX-2 | UX Update — Frontend Build | Implement the new UX changes from Figma into the actual web UI; improve spacing, typography, and responsiveness. | 8 | Completed | Will implement after UX-1 sign-off

## Sprint 3
Sprint 1 Backlog
Sprint 3 Goal(s): Deliver the core foundation of the HawkSpace app by completing essential authentication, basic room-booking functionality, and establishing the initial UI structure. By the end of Sprint 1, users should be able to log in, view available rooms, and make a simple one-time booking.
Story ID | Task ID | Task Title | Task Description | Ideal Hours | Status | Comments
Story ID | Task ID | Task Title | Task Description | Ideal Hours | Status | Comments
ADM-3 | ADM-3-T1 | Audit Trail Logging | Implement logging to record overridden booking details. | 2 | DONE | Confirm log format with team.
ADM-3 | ADM-3-T2 | Override Logic | Replace existing booking and reassign room to priority event. | 2 | DONE | Ensure conflict checks run first.
ADM-3 | ADM-3-T3 | Admin UI Override Button | Add override button and confirmation modal in admin panel. | 1 | DONE | Needs UI wireframe approval.
UI-5 | UI-5-T1 | Recurrence Options | Implement weekly & monthly recurrence selection UI. | 3 | DONE | Discuss UX for repeat selector.
UI-5 | UI-5-T2 | Create Recurring Series | Auto-generate bookings based on chosen interval. | 3 | DONE | Handle edge cases (holidays).
UI-5 | UI-5-T3 | Edit/Delete Series | Allow modifying or cancelling entire series. | 2 | DONE | Match Google Calendar-style behavior.
REP-1 | REP-1-T1 | Data Aggregation | Collect room usage data grouped by day/time. | 3 | DONE | Confirm data source fields.
REP-1 | REP-1-T2 | Visualization Setup | Build chart/table view for report display. | 3 | DONE | Decide between bar chart or heatmap.
REP-1 | REP-1-T3 | Export Report | Add ability to export report to PDF/CSV. | 2 | DONE | Ensure formatting matches admin expectations.
UI-6 | UI-6-T1 | Screen Reader Labels | Add ARIA labels and check for proper semantic structure. | 1 | DONE | Test with NVDA/VoiceOver.
UI-6 | UI-6-T2 | High Contrast Mode | Implement toggle for dark/high-contrast theme. | 1 | DONE | Ensure WCAG AA color ratios.
UI-6 | UI-6-T3 | Accessibility Testing | Run WCAG 2.1 AA compliance checks. | 1 | DONE | Document issues and fixes.